## Login page
TC_ID | TC Title | TC Scenario | TC Steps | TC Data | Priority | Severity | Expected result | Actual result | TC Status | Bug_ID
FR-1_TC1 | Secure Login | Verify that the system allows valid users to log in and blocks invalid credentials | 1. Open OrangeHRM login page. 2. Enter valid username and password. 3. Click Login. 4. Try again with invalid credentials. | username = "Admin" password= "admin123" | High | High | System allows login for valid credentials and shows an error message for invalid ones. | System successfully logged in with valid credentials and displayed an error message “Invalid credentials” for wrong input. | Pass
FR-1_TC2 | Logout Functionality | Verify that the system logs out the user and redirects to the login page | 1. Log in with valid credentials. 2. Click on the user dropdown (top right). 3. Select “Logout”. | NA | Medium | Medium | System should log out the user and redirect to the login page. | System successfully logged out the user and redirected to the login page | Pass
FR-1_TC3 | Forgot Password Link Visibility | Verify that the “Forgot your password? ” link is visible on the login page and allows users to reset their password. | 1. Open OrangeHRM login page. 2. Observe below password field for “Forgot your password?” link. 3. If available, click the link to open reset password page. | NA | High | Medium | “Forgot your password?” link should be visible and functional, allowing password reset. | “Forgot your password?” link should be visible and functional, allowing password reset | Fail | BUG-03
FR-1_TC4 | Change Password | Verify that a logged-in user can change their password successfully | 1. Log in with valid credentials. 2. Go to “My Info” or “Change Password” section. 3. Enter current password. 4. Enter new password following required format. 5. Click “Save” or “Submit”. | password = "P@assw0rd" | High | High | System should update the password and display a confirmation message. Next login should only work with the new password. | System displayed “Password changed successfully” and allowed login only with the new password. | Pass
FR-1_TC5 | Change Password | Verify that a logged-in user can change their password successfully | 1. Log in with valid credentials. 2. Go to “My Info” or “Change Password” section. 3. Enter current password. 4. Enter new password following required format. 5. Click “Save” or “Submit”. | password = "P@assw0rdpass" | High | High | System should update the password and display a confirmation message. Next login should only work with the new password. | System displayed “Password changed successfully” and allowed login only with the new password. | Pass
FR-1_TC6 | Change Password – Invalid Input | Verify that the system shows proper validation messages when incorrect or mismatched passwords are entered | 1. Log in with valid credentials. 2. Open “Change Password” page. 3. Enter wrong current password or enter different new password and confirmation. 4. Click “Save”. | password ="pass" | Medium | High | System should not change the password and should display a validation message like “Current password incorrect” or “Passwords do not match”. | System displayed error message “Passwords do not match” and prevented password update. | Pass
FR-1_TC7 | Change Password – Invalid Input | Verify that the system shows proper validation messages when incorrect or mismatched passwords are entered | 1. Log in with valid credentials. 2. Open “Change Password” page. 3. Enter wrong current password or enter different new password and confirmation. 4. Click “Save”. | password= "Passw0rd" | Medium | High | System should not change the password and should display a validation message like “Current password incorrect” or “Passwords do not match”. | System accept new password. | Fail | BUG-04
FR-2_TC1 | Book a Free Demo – Positive Flow | Verify that the system allows a user to successfully book a free demo and receive confirmation email | 1. Open OrangeHRM website. 2. Click “Book a Free Demo.” 3. Fill in all required fields (Name, Company, Email, Phone, Employees, Country). 4. Click “Submit.” |  | Medium | Medium | System should display confirmation message and send an email to schedule an appointment. | System displayed a confirmation message and sent an email to schedule an appointment | Pass
FR-2_TC2 | Contact Sales | Verify that the system allows users to contact the sales team successfully and sends a confirmation email. | 1. Open OrangeHRM homepage. 2. Click “Contact Sales”. 3. Fill in required details (Name, Email, Company, Phone, Message). 4. Click “Submit”. |  | Medium | Medium | System should display a success message and send one confirmation email to the registered email address. | System sent two identical emails when user had already booked a free demo earlier and then clicked “Contact Sales”. | Fail | BUG-01
FR-2_TC3 | open Book a Meeting link from email | Verify that the system allows users to book a only for future dates | 1Open “Book a Meeting” link from email. 2. Try selecting a past date. 3. Try selecting a future date. 4. Confirm booking. |  | Medium | Low | System should disable past dates and only allow future dates to be selected. | System correctly disabled past dates and allowed only future ones to be chosen. | Pass
FR-2_TC4 | Free Trial Registration | Verify that the system allows users to register for a 30-day free trial and sends only the relevant activation email. | 1. Open OrangeHRM homepage. 2. Click “Start Free Trial”. 3. Fill in required details (Name, Email, Company, Username, etc.). 4. Submit the form. |  | Medium | Low | System sent two emails — “Activate Your Free Trial” and “Thank You For Your Interest In OrangeHRM.” | System displayed message “You're almost there – activate your free trial” and sent activation email successfully. | Fail | BUG-02
FR-2_TC5 | Activation Link Validation | Verify that the system handles multiple activation link clicks properly (sample data / fresh options). | 1. Open the activation email. 2. Click “I like it fresh!” → observe success. 3. Click “I need sample data!” afterward. 4. Observe result. |  | Medium | Low | System should not allow another activation and may show a message like “Trial already activated.” | System displayed “Failed to create the instance .” after second click. | Pass
FR-2_TC6 | Login with Free Trial Credentials | Verify that the system allows the user to log in successfully using the credentials provided in the Free Trial activation email. | 1. Open the Free Trial activation email. 2. Copy the “Launch Free Trial” link. 3. Open it in a browser. 4. Enter Username and Password from the email. 5. Click Login. |  | Medium | Medium | System should allow successful login and display the OrangeHRM Dashboard. | System displayed the dashboard after valid credentials were entered. | Pass
FR-2_TC7 | Verify Welcome Email after Free Trial Activation | Confirm that the system sends a “Welcome to OrangeHRM” email with login credentials after the Free Trial is successfully activated. | 1. Complete Free Trial activation using the activation link. 2. Open your email inbox. 3. Check for a “Welcome to OrangeHRM” email. 4. Review the email content and verify that login credentials and launch link are included. |  | Medium | Low | System should send a “Welcome to OrangeHRM” email containing username, password, and login URL. | System sent a “Welcome to OrangeHRM” email with username, password, and login URL. | Pass
FR-2_TC8 | Number of Employees ” Field Validation | Verify that the “Number of Employees ” field in the Book a Free Demo form is selectable and allows user input. | 1. Open OrangeHRM homepage. 2. Click “Book a Free Demo.” 3. Fill all required fields except “Number of Employees.” 4. Try to select an option from the “Number of Employees” dropdown. |  | Medium | High | User should be able to select a valid number of employees from the dropdown list. | “Number of Employees” dropdown is unresponsive / cannot be selected. | Fail | BUG-05
FR-2_TC9 | Phone Number Field Missing Country Code | Verify that the “Book a Free Demo ” form allows users to enter valid phone numbers including country codes. | 1. Open OrangeHRM homepage. 2. Click “Book a Free Demo.” 3. Fill all required fields. 4. Observe the phone number field — no option for country code. |  | High | High | The field should include or auto-select the correct country code based on user’s country selection. | The phone number field does not have a country code, only plain number input allowed. | Fail | BUG-06

## authentication security
TC_ID | TC Title | TC Scenario | Preconditions | TC Steps | TC Data | Priority | Severity | Expected result | Actual result | TC Status | Bug_ID
TC_AS_001 | Password Hashing Validation | Verify that passwords are stored using hashing | System deployed and user registration available | 1. Register new user 2. Access DB (admin view) 3. Check stored password format | Password: test@123 | High | High | Passwords should be stored as hashed values (not plain text) | As Expected | Pass | N/A
TC_AS_002 | Hashing Algorithm Verification | Verify hashing algorithm (e.g., SHA-256 / bcrypt) used for password encryption | System configuration available | 1. Access encryption config 2. Verify hashing algorithm type | N/A | High | High | Passwords are encrypted using approved algorithms (SHA-256, bcrypt, etc.) | As Expected | Pass | N/A
TC_AS_003 | Password Transmission Security | Verify passwords are transmitted securely during login | System online with HTTPS enabled | 1. Use network monitor 2. Log in with valid credentials 3. Inspect network packet | Username: admin valid Password: admin123 | High | Critical | Passwords must not appear in plain text in transmission | As Expected | Pass | N/A
TC_AS_004 | Account lockout | Verify that after 3 failed login attempts, the user account is temporarily locked | OrangeHRM login page accessible | 1. Open OrangeHRM login page 2. Enter valid username with incorrect password 3 times 3. Try logging in with correct credentials | Username: emp01 invalid Password: test@123 | High | Critical | After 3 failed attempts, the account should be locked and system should display a message like “Your account is temporarily locked. Please try again later.” Correct password should not allow login until timeout | the account not locked, and after 3 failed attempts it logged without any error | failed | Bug_AS_001
TC_AS_005 | session timeout | Verify that an inactive session is automatically logged out after the configured timeout period | User logged in successfully | 1. Log in with valid credentials 2. Leave the system idle for session timeout period 3. Try performing any action after timeout | N/A | High | Critical | System should automatically log out the user. Any action after timeout should redirect to login page | As Expected | Pass | N/A
TC_AS_006 | Browser Back Button After Logout | Verify that after logout, pressing the browser back button does not display sensitive data | User logged in successfully | 1. Navigate to dashboard or sensitive pages 2. Log out 3. Press the browser back button | N/A | High | Critical | System should redirect to login page and no sensitive information should be visible | As Expected | Pass | N/A

## usability
TC_ID | TC Title | TC Scenario | Preconditions | TC Steps | TC Data | Priority | Severity | Expected result | Actual result | TC Status | Bug_ID
TC_US_001 | Verify that all pages have a clean, uncluttered, and visually consistent layout. | Verify that the website layout is clean and consistent on every page | 1- Check a stable internet. 2- Open the URL on google chrome. 3- User logged in Orangehrm as admin. | 1. Navigate through main pages. 2. Observe the layout consistency on each page. | NA | medium | minor | All pages have a clean, uncluttered design with consistent fonts, colors, spacing, and element placement | All pages have a clean, uncluttered design with consistent fonts, colors, spacing, and element placement | passed
TC_US_002 | Ensure clarify of buttons, menus, and labels. | Ensure all menus, buttons, and labels have descriptive names | 1- Set up environment. | 1. Attempt to log in with invalid credentials. 2. Observe the "Login" button and error message labels. 3. After logging in, check labels of main navigation menus and buttons. 4. Verify that labels describe their action clearly. | NA | high | major | All buttons, menus, and labels use clear, descriptive text. No ambiguous icons without tooltips. | All buttons, menus, and labels use clear, descriptive text. No ambiguous icons without tooltips. | passed
TC_US_003 | Verify main pages are accessible within 3 clicks | Check that all main features can be reached within three clicks from homepage | 1- Set up environment. 2- User logged in. | 1. From the Dashboard, count clicks to access "PIM" > "Employee List". 2. From the Dashboard, count clicks to access "Leave" > "Apply". 3. From the Dashboard, count clicks to access "Time" > "Timesheets". 4. Repeat for other main features. | NA | high | major | All main features are accessible in ≤3 clicks | All main features are accessible within 1 click | passed
TC_US_004 | Verify navigation bar consistency. | Ensure the navigation bar is consistent across all pages | 1- Set up environment. 2- User logged in. | 1. Start on the Dashboard and note the navigation bar. 2. Navigate to "PIM" > "Add Employee" and compare the bar. 3. Go to "Leave" > "My Leave" and compare again. 4. Access "Admin" > "Job Titles" and verify consistency. | NA | medium | major | The navigation bar remains identical in position, style, and functionality on all pages. | The navigation bar remains identical in position, style, and functionality on all pages. | passed
TC_US_005 | Verify ease of performing key actions for new users. | Check if new users can complete key actions without training | 1- Set up environment. 2- Use a new user account. | 1. Open login page 2. Log in or register as new user 3. Perform simple task (as: apply leave, add user, edit my info) | New user profile created | high | major | New user completes key tasks easily without external help | New users struggle with navigation and task completion (as applying leave requires trial-and-error or external assistance due to unclear workflows and lack of intuitive cues). | failed | Bug_US_01
TC_US_006 | Verify tooltips or user guidance availability | Check if first-time users receive tooltips or hints | 1- Set up environment. 2- Use a new user account. | 1. Log in as new user 2. Hover or click on input fields 3. Observe presence of hints or tooltips | New user profile created | medium | minor | Helpful tooltips or guidance appear for new users | Tooltips and hints are absent; hovering over input fields does not display helpful guidance | failed | Bug_US_02
TC_US_007 | Verify error messages for invalid input | Check that system displays clear error messages when user input is invalid | 1- Set up environment. | 1. Submit form with invalid data for example registeration 2. Observe displayed message | invalid username= " " invalid password= "1234" | high | major | System shows clear, specific error message explaining correction | System shows clear, specific error message explaining correction | passed
TC_US_008 | Verify confirmation messages after successful actions | Ensure that confirmation appears after successful operations | 1- Set up environment. 2- User logged in | 1. Submit a valid form for example add leave request 2. Observe confirmation message | NA | medium | major | Clear confirmation message appears after successful submission | Clear confirmation message appears after successful submission | passed
TC_US_009 | Verify modern and visually appealing UI | Check that the UI design is visually consistent and modern | 1- Set up environment. 2- User logged in | 1. Observe colors, icons, and layout 2. Compare with current UI/UX standards | NA | medium | minor | Interface is clean, modern, and visually appealing | Interface is clean, modern, and visually appealing | passed

## Leave management
Leave Module
TC_ID | TC Title | TC Scenario | TC Steps | TC Data | Priority | Severity | Expected result | Actual result | TC Status | Bug_ID
TC_LM_001 | Leave List | verify manager can view all leave requests All filters (Date range, Sub Unit, Location, Leave Type, Job Title, etc.) are functional and return valid results. | 1. Log in as Manager. 2. Navigate to Leave → Leave List. 3. Set the Date Range (From and To). 4. Use filters (Employee, Sub Unit, Location, Leave Type, Job Title, etc.). 5. Click Search. | NA | High | Major | The Leave List should display all employee leave requests based on the applied filters. | All filters work correctly — valid results displayed for date, location, and other filters. | pass
TC_LM_002 | Assign Leave | Verify that a manager or admin can assign leave to an employee successfully. | 1. Log in as Manager or Admin. 2. Navigate to Leave → Assign Leave. 3. Select an Employee Name. 4. Enter From Date and To Date. 5. Add Comments (optional). 6. Click Assign or Save. | NA | High | Critical | The system should successfully assign the selected leave to the employee and show a confirmation message. | Leave assigned successfully and appears in the employee’s leave list. | pass
TC_LM_003 | Bulk Assign Leave | Verify admin can assign leave to multiple employees | 1. Log in as an Employee. 2. Navigate to Leave → Apply Leave. 3. Select a leave type (e.g., PTO). 4. Enter From Date and To Date (e.g., 2025-11-10 to 2025-11-12). 5. Add a comment (optional). 6. Click Apply or Submit. | NA | High | Critical | The system should: • Accept the leave request successfully. • Show confirmation or message (e.g., “Leave applied successfully”). • Update the employee’s leave balance (e.g., PTO reduced from 11 → 8 days). • Display the request under My Leave with status “Pending Approval”. | Leave submitted successfully and visible under My Leave as “Pending Approval”. | pass
TC_LM_004 | Apply Leave | Verify that an employee can successfully apply for leave by selecting a valid leave type, entering dates, and submitting the request. | 1. Log in as Employee 2. Navigate to Leave → My Leave Usage | NA | High | Minor | The system should display all leave types with Entitlements, Pending Approval, Scheduled, Taken, and Net Balance values | Data displayed accurately — 15 days PTO with 11 remaining, and 10 sick days with 7 remaining | pass
TC_LM_005 | My Leave Usage | Verify that the “My Leave Usage” page correctly displays entitlement, pending approval, scheduled, taken, and balance values for each leave type. | 1. Log in as an Employee. 2. Navigate to Leave → My Leave Usage. 3. Observe the displayed leave types and their corresponding values. | NA | Medium | Minor | The system should correctly display all leave types with accurate values for: • Entitlements • Pending Approval • Scheduled • Taken • Net Balance | • PTO – Entitlement 15 days, Taken 4, Balance 11 • Sick Leave – Entitlement 10 days, Scheduled 3, Balance 7 | pass
TC_LM_006 | Leave Calendar | Verify calendar shows employee leaves | 1. Log in as Employee or Manager 2. Go to Leave → Leave Calendar 3.Enter name, date, or any type to search. | NA | Medium | Minor | Calendar displays all leaves thathas been taken and it types and name of employee and date | Works as expected | pass
TC_LM_007 | Verify employee leave history in “My Leave” | Validate that the employee can view their full leave records including status, type, and duration | 1. Log in as Employee 2. Navigate to Leave → My Leave 3. Review displayed leave requests and statuses | NA | Medium | Minor | The system should display all past and upcoming leave requests with correct leave type, duration, and status (Pending / Scheduled / Taken) | Leave records correctly shown: • PTO – Taken (4 days) • Sick Leave – Scheduled (3 days) • FMLA – Pending (1 day) | pass
TC_LM_008 | Entitlements | Verify admin can view and add entitlements | 1. Log in as Admin 2. Go to Leave → Entitlements | NA | Medium | Major | Entitlement list loads and updates correctly | Works as expected | pass
TC_LM_009 | Verify employee entitlements display and total calculation | Validate that the system correctly displays and totals all leave entitlements for the logged-in employee | 1. Log in as Employee 2. Navigate to Leave → Entitlements → My Entitlements 3. Review list of entitlements | NA | Medium | Minor | The system should display each leave type with entitlement amount and total days correctly calculated | Sick Leave – 10 days PTO – 15 days Total – 25 days | pass
TC_LM_010 | Verify adding a new leave entitlement | Ensure that admin can successfully add a new leave entitlement for a specific employee | 1. Log in as Admin 2. Navigate to Leave → Entitlements → Add Entitlements 3. Select employee, choose Leave Type (e.g. Annual Leave – AU), enter days, and save | NA | High | Major | The entitlement should be successfully created and appear in the Entitlement List | Entitlement successfully added and visible in list | pass
TC_LM_011 | Leave Period | Verify that the Leave Period configuration is fixed and cannot be edited once defined. | 1. Log in as Admin. 2. Navigate to Leave → Configure → Leave Period. 3. Observe the Start Month, Start Date, and End Date fields. | NA | Medium | Major | The Leave Period should be displayed correctly and remain fixed — editing or updating should be disabled. | Leave Period is visible but cannot be modified or updated. | pass
TC_LM_012 | Leave Types | Validate that all existing leave types are displayed correctly with proper attributes | 1. Log in as Admin 2. Navigate to Leave → Configure → Leave Types 3. Verify list of leave types and their attributes (Country, Duration Unit, etc.) | NA | Medium | Minor | Leave Types list should display all types with correct attribute values | Leave types displayed correctly as expected | pass
TC_LM_013 | Verify adding a new leave type | Ensure a new leave type can be added successfully | 1. Log in as Admin 2. Navigate to Leave → Configure → Leave Types 3. Click “Add” 4. Enter all required fields (Leave Type Name, Country, Duration Unit) 5. Click Save | NA | High | Major | New leave type should be added and appear in the list | New leave type added successfully | pass
TC_LM_014 | Verify validation for missing required fields in Leave Type | Ensure system prevents saving a Leave Type with missing mandatory data | 1. Click “Add” in Leave Types 2. Leave Country or Name blank 3. Click Save | NA | Medium | Major | Validation error should be displayed for required fields | Validation error displayed correctly | pass
TC_LM_015 | Verify duplication of Leave Type names across different countries | Ensure that the system handles leave types with identical names in different countries correctly. | 1.Navigate to Leave → Configure → Leave Types. 2.Click Add. 3.Enter a Leave Type name that already exists (e.g., “Annual Leave”). 4.Select a different country (e.g., France instead of Australia). 5.Save the recor | NA | High | Major | System should allow using the same Leave Type name for different countries if country-specific leave configurations are supported. | System allows creation of same Leave Type name for multiple countries (e.g., “Annual Leave – AU”, “Annual Leave – FR”). | pass
TC_LM_016 | Holidays | Verify admin can set official holidays | 1. Log in as Admin 2. Go to Leave → Configure → Holidays 3. Add holiday details | NA | Low | Minor | Holidays saved successfully | Fields are fixed (cannot edit Start Month or Date) | pass
TC_LM_017 | Verify predefined leave types and attributes | Validate that the system allows selecting multiple countries or locations for a holiday | 1. Log in as Admin 2. Navigate to Leave → Configure → Holidays 3. Click “Add” 4. Try selecting more than one country/location | NA | High | Major | System should allow selecting multiple countries or locations for one holiday entry | System allows selecting only one country/location | Fail | BUG_LM_001
TC_LM_018 | Working Weekends | Validate that all predefined leave types are listed with correct attributes | 1. Log in as Admin 2. Navigate to Leave → Configure → Leave Types 3. Observe the list of leave types and their details | NA | Medium | Minor | System should display all configured leave types (e.g., Annual Leave, Sick Leave, Maternity Leave, etc.) with correct country and duration unit | List displays correctly: - Annual Leave - AU - Compassionate Leave - AU - Maternity Leave - AU - Paternity Leave - AU - Sick Leave - AU | pass
TC_LM_019 | "Verify multiple country/location selection when adding a holiday" | Validate that the system allows selecting multiple countries or locations for a holiday | 1. Log in as Admin 2. Navigate to Leave → Configure → Holidays 3. Click “Add” 4. Try selecting more than one country/location" | NA | High | Major | System should allow selecting multiple countries or locations for one holiday entry | System allows selecting only one country/location | Fail | BUG_LM_002
TC_LM_020 | Bradford Factor Threshold | Validate that the system displays and manages Bradford Factor Thresholds correctly | 1. Log in as Admin 2. Navigate to Leave → Configure → Bradford Factor Threshold 3. Verify that thresholds (Minor, Warning, Major) and their numeric values are displayed | NA | Medium | Minor | The Bradford Factor Thresholds should display correctly with predefined values (Minor – 50, Warning – 75, Major – 100) | Thresholds displayed correctly with expected values | pass
TC_LM_021 | Notifications | Validate that admin can create and configure a leave notification successfully | 1. Log in as Admin 2. Navigate to Leave → Configure → Notifications 3. Click “Add Notification” 4. Enter all required fields (Name, Send On, Mail Subject , Leave for next X days) 5. Select filters for Job Title, Sub Unit, and Location 6. Click Save | NA | Medium | Minor | Notification should be created successfully and appear in the notification list | Notification created successfully and visible in the list | pass
TC_LM_022 | Verify Leave Calendar Configuration filters | Validate that all filters in Leave Calendar Configuration (Location, Status, Leave Type) work correctly | 1. Log in as Admin 2. Navigate to Leave → Configure → Leave Calendar 3. Select filters such as “Hide Leave with Status” and “Show Employee Leave” 4. Save and verify that the Leave Calendar updates according to selection | NA | Medium | Major | Leave Calendar view should update correctly according to applied configuration filters | Filters appear multiple times (e.g. “Hide Leave with Status” repeated) — causes confusion but works | Fail | BUG_LM_003

## user role management
Admin Module
TC_ID | TC Title | TC Scenario | Preconditions | TC Steps | TC Data | Priority | Severity | Expected result | Actual result | TC Status | Bug_ID
TC_UM_001 | Check the admin role has permissions to full access modules | Enter as admin role user and validate that admin can access and perform all available actions (assign, update, and revoke) | 1- Check a stable internet 2- Open the URL on google chrome | 1- logged user in admin role 2- navigate through each main module and check them 3- try all major actions as(add, edit, delete user) | NA | high | critical | All actions succeed without restrictions; admin can assign, update, and revoke roles. | All actions succeed without restrictions; admin can assign, update, and revoke roles. | passed
TC_UM_002 | check the ESS role has permissions to access to personal info and leave requests only | enter as ESS role user and validate that ESS can access to personal info and leave requests only | 1- set up environment 2- logged user in ESS role | 1- logged user in ESS role 2- navigate to leave request page 3- open personal info 4- try to access restricted modules(approve leave request) 5- Attempt to access User Management and assign/update a role (unauthorized action) | NA | high | critical | ESS accesses personal info and leave requests; access denied for restricted modules and role management with error messages. | ESS accesses personal info and leave requests; access denied for restricted modules and role management with error messages. | passed
TC_UM_003 | check the manager role has permissions to access to team data, leave approvals, and reports only. | enter as manager role user and validate that manager can access to team data, leave approvals, and reports. | 1- set up environment 2- logged user in manager role | 1- logged user in manager role 2- navigate to leave approval 3- navigate to team data 4- navigate to reports 5- try to access restricted modules(edit personal data info) 6- Attempt to access User Management and assign/update a role (unauthorized action) | NA | high | critical | Manager accesses team data, approvals, and reports; access denied for restricted modules and role management with error messages. | There is no manager role appeared | failed | Bug_URM_001
TC_UM_004 | validate that the user should only have one role | enter a new user and assign him to a role then try to assign more than one role to the same user | 1- set up environment 2- logged user in admin role | 1- enter user management page 2- add new user and assign to a role 3- edit the same user and try to assign to more than one role | Username: "test_u04" Role: "ESS" and "admin" | high | critical | System prevents assigning multiple roles; error message appears. | System prevents assigning multiple roles. | passed
TC_UM_005 | Ensure system allow to assign ESS role and allow to update to another role | enter a new user and assign him to ESS role then update the user to another role | 1- set up environment 2- logged user in admin role | 1- enter user management page 2- add new user and assign to ESS role 3-edit the user and assign to admin role | Username: "test_u05" Role: "ESS" New role:"admin" | high | critical | ESS assigned, updated to admin; permissions change immediately (old revoked, new active). | ESS assigned, updated to admin; permissions change immediately (old revoked, new active). | passed
TC_UM_006 | Ensure system allow to assign admin role and allow to update to another role | enter a new user and assign him to admin role then update the user to another role | 1- set up environment 2- logged user in admin role | 1- enter user management page 2- add new user and assign to admin role 3-edit the user and assign to ESS role | Username: "test_u06" Role: "Admin" New role:"ESS" | high | critical | Admin assigned, updated to ESS; permissions change immediately (old revoked, new active). | Admin assigned, updated to ESS; permissions change immediately (old revoked, new active). | passed
TC_UM_007 | Ensure system allow to assign manager role and allow to update to another role | enter a new user and assign him to manager role then update the user to another role | 1- set up environment 2- logged user in admin role | 1- enter user management page 2- add new user and assign to manager role 3-edit the user and assign to admin role | Username: "test_u07" Role: "Manager" New role:"admin" | high | critical | Manager assigned, updated to admin; permissions change immediately (old revoked, new active). | There is no manager role appeared | failed | Bug_URM_001
TC_UM_008 | Ensure that system allow to revoke roles | revoke an existing user | 1- set up environment 2- logged user in admin role | 1- enter user management page 2- revoke an existing user 3- try to log in with his username | NA | high | critical | User revoked, login fails. | User revoked, login fails. | passed
TC_UM_009 | Verify that when a user role is assigned, the action is logged in the system audit. | enter a new user and assigned to a role then check audit log page record the role assigned | 1- set up environment 2- logged user in admin role | 1- Go to User Management 2- Add a new user and assign a role 3- Navigate to the Audit Log page 4- Verify the latest entry for that user | Username: "test_u09" Role: "ESS" | high | critical | The audit log record "role assigned" with user ID, timestamp, admin, and details; read-only. | no audit found | failed | Bug_URM_002
TC_UM_010 | Verify that when a user role is updated the action is logged in the system audit. | update an existing user role then check audit log page record the role assigned | 1- set up environment 2- logged user in admin role | 1- Go to User Management 2- edit an existing user and change his role 3- Navigate to the Audit Log page 4- Verify the latest entry for that user | NA | high | critical | The audit log record "role updated" with user ID, timestamp, admin, and details; read-only. | no audit found | failed | Bug_URM_002
TC_UM_011 | Verify that when a user revoked the action is logged in the system audit. | revoke an existing user role then check audit log page record the role assigned | 1- set up environment 2- logged user in admin role | 1- Go to User Management 2- revoke an existing user 3- Navigate to the Audit Log page 4- Verify the latest entry for that user | NA | high | critical | The audit log record "user revoked" with user ID, timestamp, admin, and details; read-only | no audit found | failed | Bug_URM_002
TC_UM_012 | Verify that every user should have a role | add new user without assigning to a role then save user | 1- set up environment 2- logged user in admin role | 1- Go to User Management 2- add new user 3- fill all info except role 4- click save user btn | Username: "test_u12" Role: "" | medium | major | an error message displays that system cannot save user | System prevents assigning user without roles. | passed
TC_UM_013 | Validate Invalid Role Assignment | Attempt to assign a non-existent role to test input validation | 1- set up environment 2- logged user in admin role | 1- Go to User Management 2- add new user 3- fill role field with non-existent role 4- click save user btn | Username: "test_u13" Invalid Role: "SuperUser" | medium | major | an error message displays that system cannot save user | System prevents typing other roles roles. | passed
TC_UM_014 | Validate Mandatory Fields Before Assigning a Role | Ensure that user details must be valid before a role is assigned | 1- set up environment 2- logged user in admin role | 1- Go to User Management 2- Click "Add New User" 3- Leave username or email empty 4- Try to assign a role and click “Save” | Username: "" Email: "" Role: "Admin" | high | major | System not allow role assignment without complete and valid user info | System not allow role assignment without complete and valid user info | passed
TC_UM_015 | Prevent Admin Self-Revocation | Ensure admins cannot revoke their own role | 1- set up environment 2- logged user in admin role | 1- Go to User Management 2- Attempt to revoke current admin 3- Confirm | NA | high | critical | System prevents with error; access retained | System prevents with error; access retained | passed
TC_UM_016 | Ensure roles persist after logout/login | Assign role, log out/in, verify | 1- set up environment 2- logged user in admin role | 1- Assign ESS to the user 2- Log out 3- Log in with the same user 4- Test allowed/restricted actions | Username: "test_u16" Role: "ESS" | medium | critical | Role persists; allowed succeed, restricted fail | Role persists; allowed succeed, restricted fail | passed
TC_UM_017 | Verify that the system correctly displays and handles disabled user status | Ensure that when a user is enabled or disabled, the system updates the status correctly and applies the appropriate login permissions. | 1- set up environment 2- logged user in admin role 3- At least one existing user. | 1- Select an enabled user. 2- Disable the user and save. 3- Attempt login with that user’s data. 4- Re-enable the user and save. 5- Attempt login again with the same data. | NA | high | critical | when disabled: User can’t log in; message “Account is disabled.” when enabled: User logs in successfully. | when disabled: User can’t log in; message “Account is disabled.” when enabled: User logs in successfully. | passed

## recuirement
TC_ID | TC Title | TC Scenario | Preconditions | TC Steps | TC Data | Priority | Severity | Expected result | Actual result | TC Status | Bug_ID
TC_HR_001 | Verify HR can access job posting page | Ensure that the HR user can access the Job Posting page from the Recruitment module without error | HR is logged into the system | 1. Login as HR 2. Navigate to Recruitment module 3. Click on 'Job Vacancies' | NA | High | Critical | HR user can access job posting page successfully | HR user can access job posting page successfully | passed
TC_HR_002 | Verify HR can post a new job vacancy | Validate that HR can successfully add a new job vacancy with all required information | HR is logged into the system and navigated to Recruitment module | 1. Login as HR 2. Go to Recruitment > Job Vacancies 3. Click 'Add' 4. Fill in job details 5. Click 'Save' | NA | High | Major | New job vacancy is saved and visible in the list | New job vacancy is saved and visible in the list | passed
TC_HR_003 | Verify system validates required job fields | Ensure that the system displays appropriate error messages when required job fields are left empty | HR is on the job posting form | 1. Login as HR 2. Open job posting form 3. Leave required fields empty 4. Click 'Save' | NA | Medium | Minor | System displays validation messages for required fields | System displays validation messages for required fields | passed
TC_HR_004 | Verify job vacancy is displayed to candidates | Verify that the newly created job vacancy is visible to candidates on the Careers page | A job vacancy has been posted | 1. Login as Candidate 2. Navigate to Careers page 3. Check if newly posted job is listed | NA | High | Major | Job vacancy appears correctly for candidates | Job vacancy appears correctly for candidates | passed
TC_HR_005 | Verify HR can track candidate applications | Check that HR can view and track applications submitted by candidates | At least one candidate has applied for a vacancy | 1. Login as HR 2. Navigate to Recruitment module 3. Click on 'Candidates' 4. Check application list | NA | Low | Minor | HR can view candidate list, filter applications, and see application status | HR can view candidate list, filter applications, and see application status | passed
TC_HR_006 | Verify editing an existing job vacancy | Ensure HR can edit job details (e.g. job title, description) and save successfully | HR is logged in and a job vacancy already exists | 1. Login as HR 2. Go to Recruitment > Job Vacancies 3. Select a job vacancy 4. Click ‘Edit’ and update job details 5. Click ‘Save’ | NA | Medium | Major | The job details are updated and displayed correctly in the job list | The job details are updated and displayed correctly in the job list | passed
TC_HR_007 | Verify deleting a job vacancy | Ensure HR can delete an existing job vacancy | HR is logged in and at least one job vacancy exists | 1. Login as HR 2. Go to Recruitment > Job Vacancies 3. Select a job 4. Click ‘Delete’ 5. Confirm deletion | NA | Medium | Minor | Selected job vacancy is removed and no longer visible in the list | Selected job vacancy is removed and no longer visible in the list | passed
TC_HR_008 | Verify searching/filtering job vacancies | Validate that HR can search and filter job vacancies by job title, department, or location | HR is logged in and multiple vacancies exist | 1. Login as HR 2. Go to Recruitment > Job Vacancies 3. Use the search bar or filters 4. Click ‘Search’ | NA | High | Critical | The system displays only the filtered or searched jobs | The system displays only the filtered or searched jobs | passed
TC_HR_009 | Verify applying for a job as candidate | Ensure that candidates can apply successfully for a job vacancy | A job vacancy exists and candidate account is active | 1. Login as Candidate 2. Go to Careers page 3. Select a job 4. Click ‘Apply’ 5. Submit application form | NA | Low | Major | Candidate receives a confirmation message and application appears in HR list | Candidate receives a confirmation message and application appears in HR list | passed
TC_HR_010 | Verify validation for duplicate job entries | Check that the system prevents posting duplicate job vacancies | HR is logged in | 1. Login as HR 2. Go to Recruitment > Job Vacancies 3. Try adding a job with the same title and department 4. Click ‘Save’ | NA | Medium | Major | The system shows an error or warning message preventing duplicate entries | The system shows an error or warning message preventing duplicate entries | passed
TC_HR_011 | Verify email/notification after posting job | Ensure notification or email is triggered when a job vacancy is posted | HR is logged in and notifications are enabled | 1. Login as HR 2. Add new job vacancy 3. Click ‘Save’ 4. Check email or notification panel | NA | Medium | Critical | HR receives a notification or email confirmation | “Vacancy created successfully but no email/notification received (not supported in demo version).” | passed
TC_HR_012 | Verify job posting page responsiveness | Check that the job posting page loads correctly on different screen sizes | A job posting page is available | 1. Open job posting page 2. Resize window or open on mobile/tablet 3. Observe layout | NA | High | Major | The page layout adapts properly without errors | The page layout adapts properly without errors | passed
TC_HR_013 | Verify permission control for HR | Ensure that only users with HR role can access and post jobs | System has multiple user roles | 1. Login as a non-HR user 2. Try to access Recruitment > Job Vacancies 3. Observe access | NA | Medium | Minor | Non-HR users should be restricted from posting jobs | System allows access to Recruitment module. | failed | BUG_RE_001
TC_HR_014 | Verify candidate application status update | Ensure HR can update the application status (e.g. shortlisted, rejected) and candidate sees the change | At least one candidate applied for a job | 1. Login as HR 2. Go to Candidates list 3. Select a candidate 4. Change application status 5. Save | NA | Low | Major | The status is updated and visible in both HR and Candidate view | The page continue loading and anything didn't display | failed | BUG_RE_002

## employee info
TC_ID | TC Title | TC Scenario | TC Steps | Priority | Severity | Expected result | Actual result | TC Status | Bug_ID | Estimated time | Module | Test Type
TC_EI_001 | Verify Admin can open Add Employee form | Ensure that an authorized Admin user can successfully navigate to and open the “Add Employee” page. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify Admin can open Add Employee form | Admin was able to open the Add Employee form successfully. Form fields displayed correctly. | Pass |  | 3 | Add Employee | Positive
TC_EI_002 | Verify mandatory fields (Employee ID, First Name, Last Name) are required | Confirm that Employee ID, First Name, and Last Name are mandatory fields and cannot be left blank. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | High | Verify mandatory fields (Employee ID, First Name, Last Name) are required | Admin was not able to verify the new employee witout missing any mandatory fields. | Pass |  | 5 | Add Employee | Negative
TC_EI_003 | Verify record can be saved with valid details | Check that when all required fields are filled correctly, the employee record is successfully saved. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | High | Verify record can be saved with valid details | Succefilly saved employee | Pass |  | 5 | Add Employee | Positive
TC_EI_004 | Verify Employee ID must be unique | Validate that the system rejects duplicate Employee IDs when attempting to add a new employee. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | High | Verify Employee ID must be unique | Not able to save emplyee with repeated ID. Message "Employee id already exists" appear. | Pass |  | 5 | Add Employee | Validation
TC_EI_005 | Verify Employee ID format rule enforced | Ensure the Employee ID follows the correct format (e.g., numeric or alphanumeric based on system rules). | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Medium | Verify Employee ID format rule enforced | Employee Id must follow specified formats to be approved. | Fail | PIM_BUG-001 | 4 | Add Employee | Validation
TC_EI_006 | Verify success message appears after valid addition | Verify that a success message appears after successfully adding an employee. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Low | Verify success message appears after valid addition | Success message already appears after valid addition. | Pass |  | 3 | Add Employee | Positive
TC_EI_007 | Verify record appears in list after addition | Ensure that a newly added employee appears in the employee directory or list. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify record appears in list after addition | record appears in list after addition. | Pass |  | 4 | Add Employee | Functional
TC_EI_008 | Verify unauthorized user cannot access Add form | Check that unauthorized roles (Manager/ESS) cannot access or use the Add Employee form. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | High | Verify unauthorized user cannot access Add form | ESS employee, or anyother than Admis have no such access. | Pass |  | 5 | Add Employee | Security
TC_EI_009 | Verify error messages for missing fields | Confirm that the system shows appropriate error messages for each missing required field. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Medium | Verify error messages for missing fields | Error messages appear only for "mandatory" missing fields. | Pass |  | 4 | Add Employee | Negative
TC_EI_010 | Verify Admin can open employee record for update | Ensure Admin can access an existing employee profile and open it for editing. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify Admin can open employee record for update | Admin has the authority to open employee record for update. | Pass |  | 3 | Update Employee | Positive
TC_EI_011 | Verify Employee ID field is non-editable once saved | Validate that once an employee is created, the Employee ID cannot be modified. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | High | Verify Employee ID field is non-editable once saved | Employee ID field is editable anytime. | Fail | PIM-BUG-002 | 4 | Update Employee | Validation
TC_EI_012 | Verify editable fields can be updated and saved | Ensure that editable fields such as name, title, or department can be updated successfully. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify editable fields can be updated and saved | Verified. can be editable. | Pass |  | 4 | Update Employee | Functional
TC_EI_013 | Verify updates reflected in employee list | Confirm that any updates made to an employee’s information appear correctly in the list. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Low | Verify updates reflected in employee list | Reflected. | Pass |  | 3 | Update Employee | Functional
TC_EI_014 | Verify invalid data (email, phone) cannot be saved | Check that invalid email formats or non-numeric phone numbers are rejected by the system. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | High | Verify invalid data (email, phone) cannot be saved | A "Expected format: admin@example.com"/ "Allows numbers and only + - / ( )" messages appears on not verified data. | Pass |  | 5 | Update Employee | Validation
TC_EI_015 | Verify Manager limited update access | Confirm that Manager role can only update fields within their permission scope. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify Manager limited update access | The Manager can only update allowed fields (like personal details). Restricted fields (e.g., salary, job title, employment status) are disabled or not visible. | pass |  | 4 | Update Employee | Role-based
TC_EI_016 | Verify unauthorized user cannot update others | Check that users without update permissions are denied access to modify others’ data. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | High | Verify unauthorized user cannot update others | ESS or any unotherized employees can update only their information. | Pass |  | 5 | Update Employee | Security
TC_EI_017 | Verify search by Employee ID returns exact record | Validate that entering an Employee ID returns the exact employee record. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify search by Employee ID returns exact record | Verified. Employee returns esact record. | Pass |  | 3 | Search Employee | Functional
TC_EI_018 | Verify search by Name returns correct results | Check that searching by name returns all employees matching that name. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Medium | Verify search by Name returns correct results | Verified. Name returns esact results. | Pass |  | 3 | Search Employee | Functional
TC_EI_019 | Verify search by Job Title returns employees | Ensure that the search filter “Job Title” returns all employees with that title. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Low | Verify search by Job Title returns employees | Verified. Job returns esact employees. | Pass |  | 3 | Search Employee | Functional
TC_EI_020 | Verify search by Department returns correct employees | Confirm that department-based search filters correctly display all matching employees. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Low | Verify search by Department returns correct employees | Verified. Department returns esact employees. | Pass |  | 3 | Search Employee | Functional
TC_EI_022 | Verify partial name search works | Validate that partial name searches (e.g., “Ali” for “Alice”) return relevant matches. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Low | Low | Verify partial name search works | Verified. message returns exact match. | Pass |  | 3 | Search Employee | Functional
TC_EI_021 | Verify no results message when no match | Ensure that a clear “No records found” message appears when search yields no results. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Low | Verify no results message when no match | Verified. | Pass |  | 3 | Search Employee | Negative
TC_EI_022 | Verify Manager can search within department | Confirm that Managers can only search employees under their department. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify Manager can search within department | Verified. | Pass |  | 4 | Search Employee | Role-based
TC_EI_023 | Verify Admin can search all employees | Validate that Admin users have access to search all employee records. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | High | Medium | Verify Admin can search all employees | Verified. search returns employees. | Pass |  | 3 | Search Employee | Role-based
TC_EI_024 | Verify search performance (response time) | Ensure that search results load within acceptable response time limits (e.g., < 3 seconds). | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Low | Verify search performance (response time) | quickly (acceptable response time) Search results appeared instantly after clicking Search; system responded without noticeable delay. | Pass |  | 3 | Search Employee | Performance
TC_EI_025 | Verify names reject special characters | Ensure that employee names do not allow numbers or special symbols. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Medium | Verify names reject special characters | Names accept special characters. | Fail | PIM-BUG-004 | 3 | Validation | Validation
TC_EI_026 | Verify max character length respected | Check that input fields enforce maximum character limits defined in the SRS. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Medium | Verify max character length respected | Verified. Message "ength shouldn't exceed 30 char" appear | Pass |  | 3 | Validation | Boundary
TC_EI_027 | Verify blank optional fields accepted | Confirm that optional fields can be left blank without errors. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Low | Low | Verify blank optional fields accepted | Verified. | Pass |  | 3 | Validation | Validation
TC_EI_028 | Verify trimming of extra spaces | Ensure the system automatically trims unnecessary spaces from text inputs. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Low | Low | Verify trimming of extra spaces | No trimming of extra spaces. | Fail | PIM-BUG-003 | 3 | Validation | Validation
TC_EI_029 | Verify system handles large employee data | Validate system stability when adding or searching large employee data sets. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Medium | Verify system handles large employee data | Verified. | Pass |  | 5 | Validation | Performance
TC_EI_030 | Verify session timeout restricts access | Validate that after session timeout, user access is revoked until login again. | Step 1: Navigate to the Employee module Step 2: Perform the action Step 3: Verify outcome. | Medium | Medium | Verify session timeout restricts access | session restricts time or log in again. | Pass |  | 3 | Role-Based Access | Security